## Sheet1
SIQ_ID | Question | Answer | State | Who Asked | Who Answered | Date | Due Date | Comments (Islam) | Comments (Embedded) | Comments(QA)
SIQ_1 | What is the buzzer sequence once the temperature hits the threshold? | It's a continuous sequence that lasts for 30 seconds. | Satisfied | Kerelos Samir | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_2 | If the threshold is hit, should the counter increase immediately or after the threshold goes down? | The counter should increase immediately. | Satisfied | Kerelos Samir | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_3 | What is the response time of the buzzer after the threshold is hit? | The buzzer should work immediately. | Satisfied | Sarah Tarek | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_4 | What is the sensor readiness timing? | 30 seconds | Satisfied | Mohamed Akkary | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_5 | What is the response time of displaying the temperature on the LCD after the sensor reads the temperature? | The LCD should display the temperature immediately. | Satisfied | Sarah Tarek | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_6 | What if you changed the threshold temperature while the buzzer is already buzzing? | The buzzer Shouldn't work in the threshold edit mode | Satisfied | Kerelos Samir | Islam Yasser | 31/3/2018 | 2018-02-04
SIQ_7 | If the system moved to a cold room,will it be resetable or not ? | NO | Satisfied | Rabab Massoud | Islam Yasser | 31/3/2018 | 2018-02-04
SIQ_8 | Is there any action should happen once the buzzer hits off? As if there some warning should be sent to the customer or something? | No | Satisfied | Hanan Elshazly | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_9 | Is the sequence of the sensor as follows? 1- The sensor at the start of the system reads the temperature for 5 seconds, 2- After the first time, the sensor reads the temperature for each 30 seconds. | Yes | Satisfied | Sarah Tarek | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_10 | When the sensor reads a new temperature, Should the LCD display only the new temperature or the old and new temperatures? | Only new | Satisfied | Sarah Nagy | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_11 | If the user clicks on any two buttons at the same time, what should happen? | The first recieved signal will be executed | Satisfied | Kerelos Samir | Islam Yasser | 31/3/2018 | 2018-02-04
SIQ_12 | If the user clicks on the two buttons that are responsible for changing the threshold temperature at the same time, what should happen? | The first recieved signal will be executed | Satisfied | Sarah Tarek | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_13 | If the user clicks on one of the two buttons that are responsible for changing the threshold temperature then clicks on the other one with time between them that is less than a second, what should happen? | It should increase the threshold at first then decreased again normally | Satisfied | Sarah Tarek | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_14 | Will the system work on battery or plugged in? | Battery | Satisfied | Ahmed Haggag | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_15 | What will be the system frequency? (system clock or the crystal that generates the frequency for the system to operate) | I need more clarification | Not satisified | Nayir Michael | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_16 | What is the size of the whole module as dimensions? | I need more clarification | Not satisified | Nayir Michael | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_17 | If the user kept turning the switch ON/OFF continuously, what should happen? | The System should response normally turn on and turn off | Satisfied | Sarah Nagy | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_18 | What is the maximum of the threshold temperature? (We mean by the maximum the degree like a number 100C or etc.) | Screen size | Not satisified | Hanan Elshazly | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_19 | If the threshold is configured at a very high temperature such as 70C , should there be any action taken before it reached that specific temperature or just the buzzer hits off once the threshold is reached? | No actions needed | Satisfied | Hanan Elshazly | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_20 | What is the maximum of the counter? | Not Specified | Not Satisfied | Nayir Michael | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_21 | Is there a specific action should be taken to stop the buzzer after being fired? | move to edit mode or 30 seconds fired | Satisfied | Rabab Massoud | Islam Yasser | 31/3/2018 | 2018-02-04
SIQ_22 | What is the startup sequence? | There should be an ON/OFF switch to start the system with then a loading bar displayed on the LCD for 5 seconds while the buzzer buzzing with a sound but not a continous one. | Satisfied | Mohamed Akkary | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_23 | What should the LCD display after start up? | The temperature in the first line and the threshold in the second line. (ex: Temp: 20C Threshold: 22C) | Satisfied | Mohamed Akkary | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_24 | Where to display the counter on the LCD? And it should be displayed for how long? | It displayed in the Counter displaying mode At first line Threshold and it's counter at second line Displayed when i am in the counter displaying mode only | Satisified | Kerelos Samir | Islam Yasser | 31/3/2018
SIQ_25 | When should we reset the counter? | When the threshold is changed(reconfigured). | Satisified | Kerelos Samir | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_26 | After certain counts, should their be any actions taken by the buzzer/LCD/etc? | No | Satisfied | Sarah Tarek | Islam Yasser | 31/3/2018 | 2018-02-04
SIQ_27 | If the system resets ,would the customer like the counter to be resettable as well or should I keep the value of counter ? | Don't keep the counter value | Satisfied | Ahmed Haggag | Islam Yasser | 31/3/2018 | 2018-02-04
SIQ_28 | How to adjust the threshold temperature? | Using three buttons; the first one is to choose to adjust the threshold, the second one is to increase the threshold and the third is to decrease the threshold. | Satisified | Kerelos Samir | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_29 | How many buttons are used? | One switch to turn ON/OFF the system, three buttons; 1- To adjust between three modes(first mode: to display the temperature and threshold, second mode: to adjust the threshold, third mode: to display the counter), 2- To increse the threshold 3- To decrease the threshold | Satisified | Kerelos Samir | Islam Yasser | 31/3/2018 | 31/3/2018
SIQ_30 | It was mentioned that each 5 minutes the sensor checks how many times the threshold was hit during the 5 minutes so the counter would increase and the buzzer goes on, so Is there any other action should be taken? | What i mean is if i am exceed the threshold the counter will increse by one and if i am still above the threshold for 5 minutes so the counter should increse by 1 every 5 minutes | Satisfied | Sarah Tarek | Islam Yasser | 2018-01-04 | 2018-02-04
SIQ_31 | You mentioned that there is a Counter mode and edit mode so, there're 3 modes using one button? (Adjust threshold mode, edit the buzzer mode and display counter mode) |  | Waiting for answer | Sarah Tarek |  | 2018-02-04 | 2018-02-04
SIQ_32 | Do you mean by the edit mode is to stop the buzzer's sound before the 30 seconds? |  | Waiting for answer | Sarah Tarek |  | 2018-02-04 | 2018-02-04